## Sheet1
KENYA-SMALLSCALE AND VALUE ADDITION PROJECT (SIVAP)-RESULTS-BASED LOGICAL FRAMEWORK-UPDATED DECEMBER 2020
| Indicator | Start of Programme |  | Project Progress | [17 empty] | End of Project.
|  | Baseline | End of Prog. Target | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | EOP Target | EOP Actual
[10 empty] | 1st Half |  | 2nd Half |  | 1st Half |  | 2nd Half |  | 1st Half |  | 2nd Half |  |  |  | % PROGRESS TO TARGET
|  |  |  | Planned | Actual | Planned | Actual | Planned | Actual | Planned |  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
2.1. Increased Agricultural Productivity
2.1.1 Increased Average crop yields (mt/ha)
| Green Maize | 2.5 | 15 | 3 | 2.8 | 3.5 | 3.2 | 4 | 5 | 8 | 7.5 | 9 | 8 | 10 | 8.5 | 10 |  | 15 |  | 15 |  | 15 |  | 56.6667
| Bananas | 0 | 10 | 2 | 1.8 | 4 | 2.3 | 5 | 2.5 | 6*¹ | 4 | 6 | 4.2 | 8 | 4.8 | 8 |  | 10 |  | 10 |  | 10 |  | 48
| French Beans | 0.27 | 11 | 2 | 0.75 | 4 | 1.2 | 5 | 2.1 | 6 | 4 | 6 | 4.5 | 8 | 4.7 | 8 |  | 11 |  | 11 |  | 11 |  | 42.7273
| Water Melon | 5 | 25 | 8 | 7 | 10 | 10 | 12 | 10.5 | 15 | 11 | 15 | 12 | 20 | 12.5 | 20 |  | 25 |  | 25 |  | 25 |  | 50
| Tomatoes | 2.5 | 25 | 4 | 3.5 | 8 | 4.4 | 12 | 6.5 | 15 | 7 | 15 | 7.5 | 20 | 7.7 | 20 |  | 25 |  | 25 |  | 25 |  | 30.8
2.1.2 Increased Quantities of livestock products(Mt/yr)
| Indigenous chicken meat | 7296.9746 | 10683.5006 | 7661.8234 | 3091.44 | 8044.9145 | 3444.2568 | 8447.1603 | 3555.3 | 9000 | 3902.33 | 9000 | 4550 | 9300 | 4850 | 9300 |  | 10683.5006 |  | 10683.5006 |  | 10683.5006 |  | 45.3971
| Milk | 133552.8246 | 195534.6905 | 134888.3528 | 78342.8 | 151344.7319 | 80334.2228 | 166857.5669 | 84200.4453 | 179000 | 86403.44 | 179000 | 88505.55 | 185000 | 90500 | 185000 |  | 195534.69 |  | 195534.69 |  | 195534.69 |  | 46.2833
| Goat meat(chevon) | 3355.319 | 4912.5225 | 3388.8722 | 1766.6496 | 3802.3146 | 1884.7894 | 4192.0518 | 1904.7 | 4600 | 1951.2 | 4600 | 2202.556 | 4800 | 2350 | 4800 |  | 4912.5225 |  | 4912.5225 |  | 4912.5225 |  | 47.8369
| Honey | 1290.3482 | 1889.1988 | 1303.2517 | 599.3 | 1462.2484 | 618.6759 | 1612.1289 | 714.7 | 1700 | 753.4 | 1700 | 804.44 | 1800 | 854 | 1800 |  | 1889.1988 |  | 1889.1988 |  | 1889.1988 |  | 45.2043
| Beef | 800 | 878.3844 | 808 | 246.6 | 824.2408 | 298.6492 | 840.808 | 316.888 | 860 | 342.56 | 860 | 392.5552 | 870 | 410 | 870 |  | 878.3844 |  | 878.3844 |  | 878.3844 |  | 46.6766
| 2.1.3 Post Harvest Loss reduction in crops produced (%) | 40 | 20 | 40 | 38 | 38 | 35 | 35 | 32 | 31 | 30 | 30 | 30 | 27 | 30 | 25 |  | 22 |  | 20 |  | 20 |  | 25
| 2.1.4 Number of farmers who have adopted the technology being promoted | 6000 | 119652 | 10000 | 7000 | 20000 | 8000 | 30000 | 10000 | 60000 | 15000 | 60000 | 20000 | 90000 | 24500 | 90000 |  | 119652 |  | 119652 |  | 119652 |  | 20.476
| 2.1.5 Number of additional hectares which have adopted the technology being promoted | 200 | 2556 | 300 | 250 | 2556 | 300 | 2556 | 1356 | 2556 | 1356 | 2556 | 1360 | 2556 | 1386.48 | 2556 |  | 2556 |  | 2556 |  | 2556 |  | 54.2441
2.2 Enhanced Value Addition of crops and livestock products
| 2.2.1. Increased incomes from value added products(%) | 5 | 50 | 10 | 8 | 16 | 12 | 24 | 18 | 26 | 19 | 32 | 20 | 37 | 20.5 | 42 |  | 50 |  | 50 |  | 50 |  | 41
3.1 Irrigation Schemes constructed and rehabilitated
| 3.1.1 Percentage completion of additional area with improved/rehabilitated irrigation and drainage services | 0.078 | 100 | 20 | 10 | 50 | 30 | 70 | 35 | 80 | 41 | 90 | 45 | 95 | 46 | 100 |  | 100 |  | 100 |  | 100 |  | 46
| 3.1.2 Area with improved/rehabilitated/new irrigation and drainage services (ha) | 200 | 2556 | 511.2 | 220 | 1278 | 1546 | 1789.2 | 1586 | 2044.8 | 1600 | 2300.4 | 1640 | 2428.2 | 1660 | 2556 |  | 2556 |  | 2556 |  | 2556 |  | 64.9452
3.2 Soil and Water conservation
| 3.2.1Percentage completion of new rain fed area brought (catchments -Micro irrigation) under Irrigation (Ha) | 0 | 100 | 10 | 5% | 20% | 10% | 30% | 20% | 40% | 29% | 40 | 33 | 80 | 33 | 80 |  | 100 |  | 100 |  | 100 |  | 33
| 3.2.2 Area of new rain fed area brought (catchments -Micro irrigation) under Irrigation (Ha) | 0 | 300 | 30 | 15 | 60 | 30 | 90 | 90 | 120 | 95 | 120 | 100 | 200 | 100 | 200 |  | 300 |  | 300 |  | 300 |  | 33.3333
| 3.2.3 Design capacity (M3) of Water harvesting structures ( Water Pans (WP), Subsurface Dams (SSD) & Earth Dams (ED) Developed | 70000 | 250000 | 60000 | 50000 | 100000 | 75000 | 175000 | 100000 | 200000 | 125000 | 150000 | 125000 | 250000 | 125000 | 250000 |  | 250000 |  | 250000 |  | 250000 |  | 50
| 3.2.4 Area (ha) under soil and water conservation technologies and practices | 0 | 15000 | 1000 | 0 | 3000 | 500 | 4000 | 1235 | 6000 | 1500 | 8000 | 1550 | 10000 | 1850 | 10000 |  | 15000 |  | 15000 |  | 15000 |  | 12.3333
| 3.2.5 No of operational (BH& SW) | 0 | 60 | 0 | 0 | 20 | 0 | 30 | 0 | 40 | 18 | 40 | 19 | 50 | 19 | 50 |  | 60 |  | 60 |  | 60 |  | 31.6667
3.3 Crop and Livestock intensification and diversification
| 3.3.1 Number of demonstrations set up | 0 | 1026 | 0 | 0 | 0 | 0 | 96 | 80 | 251 | 200 | 406 | 2083 | 561 | 2093 | 716 |  | 871 |  | 1026 |  | 1026 |  | 203.9961
| 3.3.2 Number of farmers participating in the demonstrations | 0 | 18510 | 0 | 0 | 0 | 0 | 4800 | 0 | 5965 | 4000 | 7130 | 6000 | 9975 | 7085 | 12820 |  | 15665 |  | 18510 |  | 18510 |  | 38.2766
| Males | 0 | 7774.2 | 0 |  | 0 |  | 2016 |  | 2505.3 |  | 2994.6 |  | 4189.5 | 4274 | 5384.4 |  | 6579.3 |  | 7774.2
| Females | 0 | 10735.8 | 0 |  | 0 |  | 2784 |  | 3459.7 |  | 4135.4 |  | 5785.5 | 2811 | 7435.6 |  | 9085.7 |  | 10735.8
| 3.3.3 Number of farmers who have replicated the technology being promoted | 6000 | 119652 | 10000 | 7000 | 20000 | 8000 | 30000 | 10000 | 60000 | 15000 | 60000 | 20000 | 90000 | 23500 | 90000 |  | 119652 |  | 119652 |  | 119652 |  | 19.6403
4.1 Access to market
| 4.1.1 Km of rural access roads infrastructure Developed | 50 | 300 | 50 |  | 100 | 60 | 150 | 120 | 175 | 150 | 200 | 170 | 225 | 175 | 250 |  | 275 |  | 300 |  | 300 |  | 58.3333
| 4.1.2 Number of public-private agro-processing and quality control facilities installed | 0 | 16 | 0 | 0 | 0 | 0 | 6 | 5 | 8 | 6 | 8 | 6 | 12 | 6 | 12 |  | 16 |  | 16 |  | 16 |  | 37.5
4.1.3 Volume of farm produce under improved post-harvest management
| 4.1.3.1 Volume of crop farm produce under improved post-harvest management(tonnes) | 6188.6 | 38476 | 6348 | 6348 | 12177 | 8000 | 18396 | 10000 | 26683 | 13000 | 26683 | 15000 | 34719 | 16150 | 34719 |  | 38476 |  | 38476 |  | 38476 |  | 41.9742
| 4.1.3.2 Volume of Livestock farm produce under improved post-harvest management(tonnes) | 120556 | 209595 | 34868 | 20000 | 69217 | 30000 | 103955 | 50000 | 140762 | 70000 | 140762 | 80000 | 177318 | 84500 | 177318 |  | 209595 |  | 209595 |  | 209595 |  | 40.3158
| 4.1.4 Number of rural markets/market centers constructed | 0 | 22 | 0 | 0 | 0 | 0 | 15 | 10 | 12 | 11 | 12 | 11 | 20 | 11 | 20 |  | 22 |  | 22 |  | 22 |  | 50
| 4.1.5 Number of market linkages and collective marketing platforms | 0 | 96 | 0 | 0 | 8 | 0 | 9 | 6 | 12 | 7 | 20 | 9 | 40 | 11 | 80 |  | 96 | 0 | 96 | 0 | 96 |  | 11.4583
5.0 Institutional strengthening and Capacity Development
5.1 Institutional strengthening and Capacity Development | 5.1.1 Number of targeted clients who are members of an association including producer association, cooperative, water user association etc | 0 | 32392 | 1000 | 500 | 4000 | 10152 | 6500 | 10982 | 11925 | 2000 | 17350 | 3000 | 22675 | 5000 | 28000 |  | 30196 |  | 32392 |  | 32392 |  | 15.4359
| Males | 0 | 13604.64 | 420 | 2771 | 1680 | 6654 | 2730 | 7193 | 5008.5 |  | 7287 |  | 9523.5 |  | 11760 |  | 12682.32 |  | 13604.64
| Females | 0 | 18787.36 | 580 | 1546 | 2320 | 3498 | 3770 | 3789 | 6916.5 |  | 10063 |  | 13151.5 |  | 16240 |  | 17513.68 |  | 18787.36
| 5.1.2 Number off staff trained | 0 | 519 | 14 | 6 | 60 | 57 | 250 | 289 | 300 | 364 | 350 | 482 | 410*¹ | 482 | 425*² |  | 414 |  | 414 |  | 414 |  | 116.4251
| 5.1.3 Number of Community Facilitators Trained | 0 | 4725*⁴ | [10 empty] | 1500 | 0 | 1650 |  | 1575 |  | 4725 |  | 4725 |  | 0
| 5.1.4 Number of client days of training on better post-harvest storage, transportation, and/or management practices provided | 0 | 80 | 0 | 0 | 20 | 10 | 40 | 32 | 50 | 40 | 60 | 50 | 70 | 54 | 80 |  | 80 |  | 80 |  | 80 |  | 67.5
| 5.1.5 Number of beneficiaries supported by project | 6000 | 1143710*⁶ | 8000 |  | 67060 |  | 134120 |  | 221750 | 176910 | 309380 | 200000 | 579307 | 215150 | 667417 |  | 723746 |  | 1143710 |  | 1143710 |  | 18.8116
| Males | 3300 | 480358 | 3360 | 0 | 28165.2 | 0 | 56330.4 | 0 | 93135 | 74302.2 | 129939.6 | 84000 | 243308.94 | 90363 | 280315.14 | 0 | 303973.32 | 0 | 480358.2 | 0 | 480358.2
| Females | 2700 | 663352 | 4640 | 0 | 38894.8 | 0 | 77789.6 | 0 | 128615 | 102607.8 | 179440.4 | 116000 | 335998.06 | 124787 | 387101.86 | 0 | 419772.68 | 0 | 663351.8 | 0 | 663351.8
| 5.1.6 Number of client days of extension services provided to farmers | 0 | 8400 | 1000 | 500 | 2000 | 1500 | 4200 | 3832 | 6500 | 6232 | 6500 | 6432 | 7000 | 6702 | 7000 |  | 8400 |  | 8400 |  | 8400 |  | 79.7857
| 5.1.7 Number of people receiving improved nutrition services (bio-fortified foods, home gardens and utilization) | 0 | 215025*⁵ | 0 | 0 | 0 | 0 | 1100 | 1050 | 1200 | 1150 | 1500 | 1350 | 69300 | 1555 | 76050 |  | 73275 |  | 215025 |  | 215025 |  | 0.72317
| Males |  | 90311 | 0 | 0 | 0 | 0 | 462 | 441 | 504 | 483 | 630 | 567 | 29106 | 653.1 | 31941 | 0 | 30775.5 | 0 | 90310.5 | 0 | 90310.5
| Females |  | 124714 | 0 | 0 | 0 | 0 | 638 | 609 | 696 | 667 | 870 | 783 | 40194 | 901.9 | 44109 | 0 | 42499.5 | 0 | 124714.5 | 0 | 124714.5
6.1 Project Management & Cordination | 6.1.1 Operational coordination units activities | 0 | 29 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 |  | 100
| 6.1.2 Number of environmental assessement and audit ( ESMP,ESMF,EA ) | 0 | 407 | 35 | 36 | 35 | 30 | 35 | 32 | 40 | 37 | 80 | 67 | 189.5 | 151 | 299 |  | 354 |  | 407 |  | 407 |  | 10.8108
| 6.1.4 A functional M&E system | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 1 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 60
| 6.1.5 Number and cost of analytical reports/manuals published | 0 | 14 | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 6 | 2 | 7.5 | 2 | 10*³ |  | 13 |  | 14 |  | 14 |  | 14.2857
REMARKS(EXPLANATIONS)
*¹ - Additional 50 ToT staff to be trained in the 1st half of the 5th year to support Kitchen Gardening and Vegatable production and preservation.
*²- Additional 55 ToT staff to be trained in the 2nd half of the 5th year to support Kitchen Gardening and Vegatable production and preservation.
*³ -Revised to Include 2 Training Manual Developed to Support Kitchen Gardening, Agro-Processing and Value addition and another on Food and Nutrition Security from the Additonal GAFSP funding of 2M for mitigation of COVID-19 Pandemic effects
*⁴- This target is introduced as a result of the Additional 2M USD GAFSP financing.
*⁵ - This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitators from the Additional 2M USD GAFSP Financing.
*⁶ - This indicator has been revised to include additional beneficiaries arising from 109,090 Households to benefit from the Kitchen Garden Support Project but outside the current project counties (10 Counties outside the current SIVAP Project Area). Each Household as an average of 5 Members hence the total direct benficiaries outside the project counties is 109090 X5 = 545,450 beneficiaries hence making a total of 1,143,710 beneficiaries to be reached. Note the project initially targeted to reach 598,260 beneficiaries from 104,000 Households within the project area.
Note on K26: Author: 100% was not done the end of the 3rd year. So far achieved is 41%. 59% not yet done
Note on B29: Author: this includes the 60 micro-irrigation catchments
Note on K29: Author: at the end of 3rd year , the project had achieved 13%. For yr 4, 5 & 6 planning is for 87%
Note on K31: Author: At the end of yr 3, water harvesting structures were not developed but sites identification, ratification and survey works are done equating to 25%. Development will start from yr 4
Note on K32: Author: At the end of yr 3, areas to be conserved had been identified and ratified which equates to 10%. Conservation works to be done from yr 4.
Note on K33: A
Note on D52: KNH: Revised to include additional 105 ToTs to be trained on Kitchen gardening, vegetable production etc arising from additional 2M USD funding from GAFSP towards mitigation of COVID-19 pandemic effects in agricultural sector.
Note on O52: KNH: Includes an increased target of 50 ToT staff Trained in the 1st Half on Kitchen Gardening and Vegetable Preservation arising from additional GAFSP funding of 2M USD.
Note on Q52: KNH: ncludes an increased target of 55 ToT staff Trained in the 2nd Half on Kitchen Gardening and Vegetable Preservation arising from additional GAFSP funding of 2M USD.
Note on D53: KNH: This target is introduced as a result of the Additional 2M USD GAFSP financing.
Note on O53: KNH: KNH: Revised to include additional 105 ToTs to be trained on Kitchen gardening, vegetable production etc arising from additional 2M USD funding from GAFSP towards mitigation of COVID-19 pandemic effects in agricultural sector.
Note on Q53: KNH: KNH: Revised to include additional 105 ToTs to be trained on Kitchen gardening, vegetable production etc arising from additional 2M USD funding from GAFSP towards mitigation of COVID-19 pandemic effects in agricultural sector.
Note on S53: KNH: KNH: Revised to include additional 105 ToTs to be trained on Kitchen gardening, vegetable production etc arising from additional 2M USD funding from GAFSP towards mitigation of COVID-19 pandemic effects in agricultural sector.
Note on U53: KNH: KNH: Revised to include additional 105 ToTs to be trained on Kitchen gardening, vegetable production etc arising from additional 2M USD funding from GAFSP towards mitigation of COVID-19 pandemic effects in agricultural sector.
Note on W53: KNH: KNH: Revised to include additional 105 ToTs to be trained on Kitchen gardening, vegetable production etc arising from additional 2M USD funding from GAFSP towards mitigation of COVID-19 pandemic effects in agricultural sector.
Note on D55: KNH: his indicator has been revised to include additional beneficiaries arising from 109,090 Households to benefit from the Kitchen Garden Support Project but outside the current project counties (10 Counties outside the current SIVAP Project Area). Each Household as an average of 5 Members hence the total direct benficiaries outside the project counties is 109090 X5 = 545,450 beneficiaries hence making a total of 1,143,710 beneficiaries to be reached. Note the project initially targeted to reach 598,260 beneficiaries from 104,000 Households within the project area.
Note on O55: KNH: his indicator has been revised to include additional beneficiaries arising from 109,090 Households to benefit from the Kitchen Garden Support Project but outside the current project counties (10 Counties outside the current SIVAP Project Area). Each Household as an average of 5 Members hence the total direct benficiaries outside the project counties is 109090 X5 = 545,450 beneficiaries hence making a total of 1,143,710 beneficiaries to be reached. Note the project initially targeted to reach 598,260 beneficiaries from 104,000 Households within the project area.
Note on Q55: KNH: his indicator has been revised to include additional beneficiaries arising from 109,090 Households to benefit from the Kitchen Garden Support Project but outside the current project counties (10 Counties outside the current SIVAP Project Area). Each Household as an average of 5 Members hence the total direct benficiaries outside the project counties is 109090 X5 = 545,450 beneficiaries hence making a total of 1,143,710 beneficiaries to be reached. Note the project initially targeted to reach 598,260 beneficiaries from 104,000 Households within the project area.
Note on S55: KNH: his indicator has been revised to include additional beneficiaries arising from 109,090 Households to benefit from the Kitchen Garden Support Project but outside the current project counties (10 Counties outside the current SIVAP Project Area). Each Household as an average of 5 Members hence the total direct benficiaries outside the project counties is 109090 X5 = 545,450 beneficiaries hence making a total of 1,143,710 beneficiaries to be reached. Note the project initially targeted to reach 598,260 beneficiaries from 104,000 Households within the project area.
Note on U55: KNH: his indicator has been revised to include additional beneficiaries arising from 109,090 Households to benefit from the Kitchen Garden Support Project but outside the current project counties (10 Counties outside the current SIVAP Project Area). Each Household as an average of 5 Members hence the total direct benficiaries outside the project counties is 109090 X5 = 545,450 beneficiaries hence making a total of 1,143,710 beneficiaries to be reached. Note the project initially targeted to reach 598,260 beneficiaries from 104,000 Households within the project area.
Note on W55: KNH: his indicator has been revised to include additional beneficiaries arising from 109,090 Households to benefit from the Kitchen Garden Support Project but outside the current project counties (10 Counties outside the current SIVAP Project Area). Each Household as an average of 5 Members hence the total direct benficiaries outside the project counties is 109090 X5 = 545,450 beneficiaries hence making a total of 1,143,710 beneficiaries to be reached. Note the project initially targeted to reach 598,260 beneficiaries from 104,000 Households within the project area.
Note on D59: KNH: This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitatots from the Additional 2M USD GAFSP Financing
Note on O59: KNH: This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitatots from the Additional 2M USD GAFSP Financing
Note on Q59: KNH: This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitatots from the Additional 2M USD GAFSP Financing
Note on S59: KNH: This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitatots from the Additional 2M USD GAFSP Financing
Note on U59: KNH: This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitatots from the Additional 2M USD GAFSP Financing
Note on W59: KNH: This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitatots from the Additional 2M USD GAFSP Financing
Note on D60: KNH: This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitatots from the Additional 2M USD GAFSP Financing
Note on D61: KNH: This Indicator has been revised to include additional 212,625 people who will receive trainings on improved nutrition services from the community facilitatots from the Additional 2M USD GAFSP Financing
Note on F63: Author:Janet - 6 ESMPs prepared for 6 Irrigation schemes ( Makanyaga, Kirumi, Kyee Mwee, Rubiru and Kaboson, Ruungu) - 20 ESMP monitoring/ Envtal Audits: Thru 4 quartely Construction phase ESMP monitoring by 5 consultants*5 schemes - 10 ESMP monitoring/EA: Thru Regular monitoring by PCU during site management meetings
Note on H63: Author:Janet - 20 ESMP Monitoring/Envtal Audits: Thru 4 quartely Construction phase ESMP monitoring by 5 consultants*5 schemes - 10 ESMP Monitorig/ EA: Thru Regular monitoring by PCU during site management meetings in the 5 schemes ( Makanyaga, Kirumi, Ruungu, Rubiru and Kaboson)
Note on J63: Author: Janet - 6 ESMP Prepared for 6 Irrigation schemes ( Buuri, Utangwa, Oleshonko, Kagogo Wendani, Gikindu, Ndiriti Aguthi) - 16 ESMP Monitoring/Envtal Audits: Thru 4 quartely Construction phase ESMP monitoring by 4 consultants*4 schemes ( Ruungu, Makanyaga, Kirumi, Kaboson) Note: Rubiru construction stopped) - 10 ESMP monitoring/ EA: Thru Regular monitoring by PCU during site management meetings
Note on L63: User:Janet - 4 Annual EA undertaken for 4 Irrigation schemes ( Ruungu, Makanyaga, Kirumi and Kaboson) - 13 ESMP prepared for 7 BH ( Kithimani Primary, Matinga primary, Iiani primary, Matheani Primary, Kwa Kang’ethe Kiswa, Mbukoni Kwa Musyoka Muatha, Kwa Nzasi all in Kitui); 3 ED (Kwa Mbunza /Masilingini; Kitula; Masia -Kwa Kauwi all in Kitui); 2 SSD (Kwa Ngeta; Kwa Kathanzu all in Kitui) and 1 Livestock Sale Yard ( Kathonzweni in Makueni) - 10 site management meetings NOTE: 1. Rubiru contractor and consultants were terminated 2. NO funds during the first quarter of FY 2019/20
Note on B65: KNH: Revised to Include 2 Training Manual Developed to Support Kitchen Gardening, Agro-Processing and Value addition and another on Food and Nutrition Security from the Additonal GAFSP funding of 2M for mitigation of COVID-19 Pandemic effects
Note on D65: KNH: Revised to Include 2 Training Manual Developed to Support Kitchen Gardening, Agro-Processing and Value addition and another on food and Nutrition Security form the Additonal GAFSP funding of 2M for mitigation of COVID-19 Pandemic effects
Note on Q65: KNH: Revised to Include 2 Training Manual Developed to Support Kitchen Gardening, Agro-Processing and Value addition and Food and Nutrition Security from the Additonal GAFSP funding of 2M for mitigation of COVID-19 Pandemic effects